## Issues Log
PROJECT ISSUES LOG
Track and resolve project issues before they become major problems
Project Name: | [Enter Project Name] |  |  | Grant/Award #: | [Enter Award Number] |  |  | Last Updated: | 01/07/2026
Issue ID | Date Raised | Issue Category | Issue Description | Priority | Impact | Assigned To | Target Resolution | Actual Resolution | Status | Resolution Action | Notes
I-001 | 01/10/2026 | Compliance | Missing environmental clearance documentation | Urgent | Cannot proceed with construction until resolved | [Environmental Specialist] | 01/20/2026 |  | Open | Contact state agency for status; prepare supplemental docs if needed | Escalate if not resolved by 01/15
I-002 | 01/12/2026 | Procurement | Only one bid received for construction contract | High | May need to re-advertise, causing 30-day delay | [Procurement Officer] | 01/25/2026 |  | In Progress | Extend bid deadline by 2 weeks; expand advertising to adjacent counties | Check COBID for certified firms
I-003 | 01/14/2026 | Budget | Engineer's estimate $15,000 higher than budget | Medium | May need to reduce scope or request budget modification | [Project Manager] | 02/01/2026 |  | Open | Review scope for potential reductions; contact grant manager about options | Value engineering session scheduled
I-004 | 01/08/2026 | Communication | Key stakeholder not receiving project updates | Low | Stakeholder may not support project decisions | [Communications Lead] | 01/15/2026 | 01/14/2026 | Closed | Added to distribution list; scheduled monthly check-in calls | Verified receipt of last two updates
I-005 | 01/16/2026 | Technical | Geotechnical report shows unexpected soil conditions | High | May require foundation design changes and additional cost | [Engineer of Record] | 01/30/2026 |  | In Progress | Engineer reviewing options; request preliminary cost estimate for changes | Meeting with contractor 01/18
I-006
I-007
I-008
I-009
I-010
I-011
I-012
I-013
I-014
I-015
I-016
I-017
I-018
I-019
I-020
I-021
I-022
I-023
I-024
I-025

## Categories & Priority
ISSUE CATEGORIES
Category | Description
Compliance | Issues related to federal/state grant requirements
Procurement | Issues with bidding, contracting, or vendor management
Budget | Cost overruns, funding gaps, or budget concerns
Schedule | Delays or timeline conflicts
Technical | Design, engineering, or construction problems
Communication | Stakeholder or team communication gaps
Resource | Staff, equipment, or material availability
Quality | Work quality or specification compliance
External | Issues caused by factors outside project control
PRIORITY LEVELS
Priority | Response Time
Urgent | Immediate action required; project stopped or at risk of major failure
High | Action needed within 1 week; significant impact on schedule/budget/scope
Medium | Action needed within 2-4 weeks; moderate impact if not resolved
Low | Address when convenient; minimal impact on project
STATUS OPTIONS
Status | Definition
Open | Issue identified but work not yet started
In Progress | Actively working on resolution
Pending | Waiting for external input or decision
Escalated | Elevated to higher authority for resolution
Closed | Issue resolved and documented

## Issue vs Risk
ISSUES vs. RISKS: WHAT'S THE DIFFERENCE?
ISSUES
Problems that are happening NOW
Require immediate attention and action
Track in the Issues Log
Focus: Resolution
Example: The contractor submitted incomplete Davis-Bacon documentation.
RISKS
Problems that MIGHT happen in the future
Can be planned for and mitigated
Track in the Risk Register
Focus: Prevention
Example: The contractor might submit incomplete Davis-Bacon documentation.
KEY POINT
When a risk actually occurs, it becomes an issue. Move it from the Risk Register to the Issues Log and focus on resolution.
FEDERAL COMPLIANCE TIP
Document all issues and their resolutions in your project files. Grant auditors will want to see how you identified and addressed problems during the project.