## Lessons Learned
LESSONS LEARNED REGISTER
Capture knowledge to improve future projects
Project Name: | [Enter Project Name] |  |  | Grant/Award #: | [Enter Award Number] |  |  | Project End Date: | [MM/DD/YYYY]
LL ID | Date Recorded | Project Phase | Category | Type | What Happened | Impact | Root Cause | Recommendation | Applicable To | Recorded By
LL-001 | 01/15/2026 | Planning | Compliance | Success | Submitted environmental review docs 60 days before planned construction start | Environmental clearance received on schedule; no construction delays | Project manager had experience with similar project and knew typical review times | Build in minimum 60-day buffer for environmental reviews on similar projects | All federally funded projects | [Project Manager]
LL-002 | 02/01/2026 | Procurement | Procurement | Improvement | Only received one bid on first advertisement for construction contract | Had to extend bid period by 3 weeks, delaying project start | Advertisement only placed in local newspaper; limited contractor pool in rural area | Advertise on state procurement website, COBID, and in regional publications; reach out to known contractors directly | Rural infrastructure projects | [Procurement Officer]
LL-003 | 03/15/2026 | Execution | Budget | Success | Monthly budget tracking meetings caught potential overrun early | Identified $8,000 overage in materials; worked with contractor to value engineer solution | Regular monitoring allowed early detection and time to find alternatives | Hold monthly budget review meetings with contractor and grant administrator | All construction projects | [Grant Administrator]
LL-004 | 04/01/2026 | Execution | Communication | Improvement | Contractor submitted change order without prior discussion | Created confusion about scope; required emergency meeting with grant manager | Change order process not clearly explained at pre-construction meeting | Include detailed change order procedures in pre-construction meeting agenda; provide written protocol to contractor | All construction contracts | [Project Manager]
LL-005 | 05/15/2026 | Closeout | Documentation | Success | Maintained organized digital files throughout project with consistent naming convention | Closeout documentation compiled in 2 days instead of typical 2 weeks | File organization system established at project start and maintained consistently | Create file structure template at project start; train all team members on naming conventions | All grant-funded projects | [Administrative Assistant]
LL-006
LL-007
LL-008
LL-009
LL-010
LL-011
LL-012
LL-013
LL-014
LL-015
LL-016
LL-017
LL-018
LL-019
LL-020
LL-021
LL-022
LL-023
LL-024
LL-025

## Categories & Guidance
LESSONS LEARNED CATEGORIES
Category | Topics Covered
Planning | Project initiation, scope definition, scheduling, budgeting
Compliance | Federal/state requirements, environmental review, labor standards
Procurement | Bidding, contractor selection, contract management
Budget | Cost management, change orders, financial reporting
Schedule | Timeline management, milestone tracking, delays
Communication | Stakeholder engagement, team coordination, reporting
Technical | Design, engineering, construction methods
Documentation | Record keeping, file management, audit preparation
Closeout | Final inspections, reporting, grant closeout procedures
LESSON TYPES
Type | Description
Success | Something that worked well and should be repeated
Improvement | Something that could be done better next time
PROJECT PHASES
Phase | Activities
Initiation | Project start-up, grant award acceptance, team formation
Planning | Detailed planning, environmental review, permitting
Procurement | Bidding, contractor selection, contract execution
Execution | Construction, implementation, ongoing management
Monitoring | Progress tracking, compliance checks, reporting
Closeout | Final inspections, documentation, grant closeout

## How to Capture
HOW TO CAPTURE LESSONS LEARNED
WHEN TO CAPTURE LESSONS
• After completing a major project phase or milestone
• When something unexpectedly good or bad happens
• During regular project status meetings (make it a standing agenda item)
• When resolving significant issues
• At project closeout (comprehensive review)
• When receiving feedback from stakeholders
QUESTIONS TO ASK
What went well? | Identify successes to repeat on future projects
What could have gone better? | Identify areas for improvement
What surprised us? | Uncover assumptions that proved wrong
What would we do differently? | Capture specific actionable changes
What should others know? | Consider who else could benefit from this knowledge
TIPS FOR EFFECTIVE LESSONS
• Be specific - avoid vague statements like 'communication was poor'
• Focus on the process, not blame - what can we change, not who made a mistake
• Include context - what were the circumstances?
• Make recommendations actionable - what exactly should someone do?
• Record lessons promptly - details fade over time
• Share with the team - lessons learned in private don't help others
FEDERAL GRANT TIP
Many federal grants require a final report that includes lessons learned. Capturing them throughout the project makes this report much easier to complete and more valuable.

## Common Lessons
COMMON LESSONS FROM INFRASTRUCTURE PROJECTS
Learn from others' experience - these issues come up frequently
Environmental Review
• Start environmental review as early as possible - it often takes longer than expected
• Identify all required permits before finalizing project schedule
• Coordinate with multiple agencies simultaneously when possible
Procurement
• Rural areas may have limited contractor pool - plan for extended bid periods
• Pre-qualify contractors when allowed to reduce bid evaluation time
• Include clear Davis-Bacon requirements in bid documents
Budget Management
• Include adequate contingency (10-15%) for unexpected costs
• Track expenditures against budget weekly during construction
• Document all cost changes, even small ones
Schedule Management
• Build weather delays into construction schedules
• Identify long-lead items early and order promptly
• Have backup plans for critical path activities
Compliance
• Conduct Davis-Bacon training for contractors before work starts
• Review certified payrolls weekly, not just at project end
• Keep compliance documentation organized throughout project
Stakeholder Management
• Communicate early and often, even when there's no news
• Document all stakeholder commitments and decisions
• Address concerns promptly before they escalate
Documentation
• Establish file organization system at project start
• Use consistent naming conventions for all documents
• Back up files regularly and in multiple locations
Closeout
• Begin closeout preparation 60 days before project end
• Conduct final inspection before making final payment
• Submit final reports promptly to avoid grant closeout issues