## 5x5 Risk Matrix
RISK ASSESSMENT MATRIX (5x5)
State & Federally Funded Infrastructure Projects
PROBABILITY / IMPACT MATRIX
IMPACT
|  | 1 Insignificant | 2 Minor | 3 Moderate | 4 Major | 5 Severe
P | 5 - Almost Certain (>90%) | 5 | 10 | 15 | 20 | 25
| 4 - Likely (60-90%) | 4 | 8 | 12 | 16 | 20
| 3 - Possible (30-60%) | 3 | 6 | 9 | 12 | 15
| 2 - Unlikely (10-30%) | 2 | 4 | 6 | 8 | 10
| 1 - Rare (<10%) | 1 | 2 | 3 | 4 | 5
RISK LEVEL LEGEND
Level | Score Range | Response Guidance
Critical | 16-25 | Immediate action required; may stop work until resolved
High | 9-15 | High priority; develop response plan within 1 week
Medium | 4-8 | Moderate priority; monitor closely, plan mitigation
Low | 1-3 | Low priority; monitor, accept or document

## Probability Scale
PROBABILITY SCALE - DETAILED CRITERIA
Score | Level | Likelihood | Infrastructure Project Indicators
5 | Almost Certain | >90% likely to occur | Has happened on most similar projects; current conditions strongly favor occurrence; multiple warning signs present
4 | Likely | 60-90% likely to occur | Has happened on several similar projects; conditions favor occurrence; some warning signs present
3 | Possible | 30-60% likely to occur | Has happened occasionally on similar projects; equal chance of occurring or not; circumstances could develop
2 | Unlikely | 10-30% likely to occur | Has rarely happened on similar projects; unlikely but possible; requires unusual circumstances
1 | Rare | <10% likely to occur | Has almost never happened; highly improbable; would require extraordinary circumstances
TIPS FOR ASSESSING PROBABILITY
• Consider your organization's history with similar projects
• Check with regional partners about their experience
• Review lessons learned from past projects
• Consider current economic and regulatory conditions
• Factor in your team's experience level
• Be honest - overconfidence leads to poor planning

## Impact Scale
IMPACT SCALE - DETAILED CRITERIA
Score | Level | Budget Impact | Schedule Impact | Scope Impact | Compliance Impact
5 | Severe | >25% budget overrun or project failure | >6 months delay or project cancellation | Major deliverables eliminated; project does not meet basic objectives | Grant funds must be returned; legal action; debarment risk
4 | Major | 15-25% budget overrun | 3-6 months delay | Significant scope reduction; key deliverables affected | Major audit findings; grant conditions added; close monitoring required
3 | Moderate | 5-15% budget overrun | 1-3 months delay | Some scope items reduced or modified | Minor audit findings; corrective action required
2 | Minor | <5% budget overrun | <1 month delay | Minor adjustments to deliverables | Documentation issues; process improvements needed
1 | Insignificant | Within budget contingency | Within schedule float | No meaningful impact on deliverables | No compliance impact
FEDERAL COMPLIANCE NOTE
For federally funded projects, compliance impacts can be the most significant. Common compliance failures that result in returned grant funds include: starting work before environmental clearance, failing to use competitive procurement, Davis-Bacon violations, and unauthorized scope changes.

## Scoring Examples
RISK SCORING EXAMPLES - INFRASTRUCTURE PROJECTS
Learn to apply the matrix by reviewing these common infrastructure project risks
Risk | Probability | Impact | Score | Rationale
Environmental review delays construction start | 4 | 4 |  | Likely (happens on ~70% of projects in our area); Major impact (could delay 3+ months)
Construction bids exceed budget by >10% | 3 | 4 |  | Possible (happened on about half of recent projects); Major impact (may require scope reduction or additional funding)
Contractor submits incomplete Davis-Bacon payroll | 4 | 3 |  | Likely (most contractors need reminders); Moderate impact (delays payment, requires correction)
Key project staff leaves during execution | 2 | 4 |  | Unlikely (our turnover is low); Major impact (could significantly delay project)
Bad weather delays construction | 3 | 2 |  | Possible (normal for our region); Minor impact (schedule has weather contingency built in)
Unexpected soil conditions found | 2 | 5 |  | Unlikely (geotechnical report was thorough); Severe impact (major redesign and cost increase)
Community opposition to project | 1 | 3 |  | Rare (strong community support documented); Moderate impact (could delay permits if it occurred)
Material delivery delays | 3 | 3 |  | Possible (supply chain issues ongoing); Moderate impact (could delay 1-2 months)
KEY TAKEAWAY
Risk assessment is subjective, but should be based on evidence (past experience, industry data, expert judgment). Document your rationale so others can understand and review your assessments.